## CC Discussion Topic Tacker
CC Meeting Discussion Topics Status Tracker
Source | Topic # | Topic Summary Note: These summaries are compilations/paraphrasing of issues raised by CC members--not the positions of the CC | History of Discussion | Proposal Form Received for This Topic | Notes | Level of Resolution as of 3/30/16 Mtg | Possibly Only Clarifiations Required to Resolve | Further Substantive Discussion Required | Further Discussion Pending Regulatory Clarification | Agree to Raise Issue in BP as Issue Deserving CPUC Attention | Agree to Advocate for Issue After BP Submittal | CC Members Agree to Disagree | Agree to Disagree Given Available Information | Rejected As Out of Scope for CC
Coalition Proposal 3/15/16 @ CC Mtg | 1 | Simplification of Portfolio -- Need to simplify from "150" to fewer programs, but make programs more flexible. There are too many programs making them difficult to follow and hard to understand for many potential program participants resulting in lower customer uptake | Discussed in CC Mtgs 3/15, 3/30, 4/20 |  | Task Force created in 4/20 cc meeting to further define proposal. Bernie Kotlier is point person | Open |  | X
Coalition Proposal 3/15/16 @ CC Mtg | 2 | Meter Savings as Key Approach -- Most resource programs going forward should be based on metered savings for med-large Comm/industrial and institutional | Discussed in CC Mtgs 3/15, 3/30 |  | More conversation pending regulatory guidance/decision, but there was consensus that it was important strategy and should be discussed in BP. | Open |  |  | X
Coalition Proposal 3/15/16 @ CC Mtg | 3 | O&M -- Support behavioral and operational measures focused on WE&T aspects Example: CCC and CLTC at Davis | Discussed in CC Mtgs 3/15, 3/30 |  | Delegated as recommendation to subcommittee: Large majority of CC members supported sharing this recommendation with the WE&T subcommittee though not a consensus decision | Provisionally closed | [6 empty] | X
Coalition Proposal 3/15/16 @ CC Mtg | 4 | Reorienting to Controls -- The current portfolio is too widget-based. Large opportunities remain with controls, and the Business Plan needs to address controls much more aggressively than is currently the case. | Discussed in CC Mtgs 3/15, 3/30 |  | Unanimous agreement that controls are a good opportunity, but current policy doesn't allow desired changes. Send guidance to Subcommittees | Provisionally closed |  |  | X
Coalition Proposal 3/15/16 @ CC Mtg | 5 | Workforce Standards -- Programs shall have workforce standards based on certification, minimum performance standards, and pre-qualification process for programs that are not customer DIY type programs. | Discussed in CC Mtgs 3/15, 3/30 |  | Need to further discuss non-permit issues? | Open | X
Coalition Proposal 3/15/16 @ CC Mtg | 6 | Launch MUSH and MF affordable programs -- There are too many missed opportunities in ratepayer programs for both greater savings and public equity in Municipal, University, School, and Hospital (MUSH) market segments, as well as office buildings. | Discussed in CC Mtgs 3/15, 3/30, 4/20 |  | Discussed in 4/20 meeting. It was agreed to send this topic to Public Sector subcommittee rather than creating a task force | Open |  | X
Coalition Proposal 3/15/16 @ CC Mtg | 7 | Statewide Programs -- Statewide Programs should be administered by a single PA on behalf of all CPUC overseen territory and possibly by a single implementer, depending on program type. | Discussed in CC Mtg 3/15, 3/30 and 4/20 |  | Discussed in 4/20 meeting. Pending PA confirmation that no regulatory barriers exist for PAs voluntarily cost-sharing and acting on behalf of other PAs for statewide administration. Otherwise pending CPUC decision on statewide progarm administration this summer. | Open |  |  | X
Coalition Proposal 3/15/16 @ CC Mtg | 8 | WE&T Alignment with Programs -- Workforce develoment, training and job creating needs to be aligned with programs. Connect disadvantaged workers to middle class jobs. Prioritize funding for skills-building training that is linked to actual employment and leverages college, apprenticeship and labor-management training | Discussed in CC Mtgs 3/15, 3/30 |  |  | Open |  | X
MCE Discussion 3/15/16 @ CC Mtg | 9 | MCE to be Default Administrator -- In order to be able to achieve portfolio cost-effectiveness, MCE proposes to become default administrator of EE programs in it's cities in which it operates subject to various qualifications. In those cities where it becomes default operator, it would address both IOU and MCE customers to maximize efficiency and reduce confusion. MCE would elect not to administer certain programs that don't make sense (e.g., certain upstream programs), but generally wishes to position itself as a single point of contact (at least) for most program services. | Discussed in CC Mtgs 3/15, 3/30 |  |  | Closed | [6 empty] | X
Coalition Proposal 3/15/16 @ CC Mtg | 10 | Building permits required--All programs containing work that needs a building permit must be permitted and have proof of passing inspection before incentive is paid or creditied to customer or service provider. This proposal increases compliance rigour over current PA practice of requiring participants declare that they have obtained all necessary permits. This concept is also the subject of legislation in play in Sacramento at this time. | Discussed in CC Mtgs 3/15, 3/30, 4/20 |  | Widely agreed that building permit compliance is important. How that should affect program design and PA role in compliance is at issue. | Provisionally closed | [6 empty] | X
CEEIC & Coalition Proposal | 11 | Defined program turnover-- A specific % of portfolio to be rebid/recontracted in each of the next several years (proposed to bid ~1/4 of portfolio each year, e.g., all Commercial programs in 2017) | Discussed in CC Mtgs 3/15, 3/30, 4/20 |  | Task Force created in 4/20 cc meeting to further define proposal. Bernie Kotlier is point person | Open |  | X
Coalition Proposal 3/15/16 @ CC Mtg | 12 | Independent Evaluator -- An independent proposal review and selection consultant should be hired to provide oversight of implementer proposals review and selection. | Discussed in CC Mtgs 3/15, 3/30, 4/20 |  | Task Force created in 4/20 cc meeting to further define proposal. Bernie Kotlier is point person | Open |  | X
Coalition Proposal 3/15/16 @ CC Mtg & CEEIC March 4th letter | 13 | Administration versus Implementation -- A bright line shall be established and utilized to differentiate between administration and implementation of IOU programs. PAs handle program administration, implementation activities should be outsourced by PAs. To consider and achieve that goal, the business plans should chart a path toward outsourcing work (both “core” and third party program work) that is not administration. We understand that this might have to be phased-in, but it should be the goal and intent to make it happen within a short time frame. The business plans need articulate how that transition will be accomplished. | Discussed in CC Mtgs 3/15, 3/30, 4/20 | Yes | Task force creatd in 4/20 CC meeting to further define proposal. Margie Gardner is point person. | Open |  | X
Coalition Proposal 3/15/16 @ CC Mtg | 14 | Providing opportunities for disadvantaged communities/EJ — Coalition | Discussed in CC Mtgs 3/15, 4/20 |  | Task force creatd in 4/20 CC meeting to further define proposal. Carmalita is point person. | Open |  | X
Facilitator synthesized this from numerous PA and stakeholder comments in 2/22 and 2/23 meetings | 15 | Data challenge discussions. PAs lack access to current adequate market characteriziation, saturation, market share, field monitoring, EUL and other data. CEUS and RASS studies are very out of date, especially with respect to fast evolving measures, such as plug loads. Data problems particularly confound plans to move to existing baseline for voluntary programs and would be instrumental for advancing C&S and ET programs. The CEUS, RASS and other studies that are designed based on sampling to represent IOU service territories may not provide enough statistically significant data for smaller service territories such as MCE and don't yield locally differentiated data useful for programs serving distribution constrained areas. CEC is responsible for these studies, but it's objective is provision of data for Load Forecasting and likely cannot justify the additional cost of expanding the scope of these studies to meet this need. | Discussed in February Sector Mtgs and 4/20 CC mtg |  | Need for task force considered in 4/20 CC meeting. Facilitator to check in with stakeholders to assess interest. | Open |  | X
SoCalREN | 16 | PA Business Plan Review Criteria for Stakeholders | Topic discussed in Public Sector SC Mtg 3/15 and 4/20 CC mtg | Yes |  | Open | X
CC / Com SC Meeting 2/22/16 | 17 | RCx -- What is role of retrocommissioning (hereafter “RCx”) in the future plan? [Commercial & Industrial sector, primarily] | Discussed in Feb CC Mtg |  |  | Open |  |  |  | X | X
Expected in April from ED | 18 | Updated ED guidance on BP outline |  |  |  | Open |  | X
CC Meeting 3/30 Discussion | 19 | What kind of decisions can CC be expected to make and how can CC address issues that are important to large majorities of CC members but can't reach consensus | Discussed in CC Mtg 3/15, 3/30 and 4/20 |  | Coalition for EE objects on record to current process and stucture of the CC with respect to ability to direct focus of Subcommittees. | Provisionally closed | [5 empty] | X
Foot Notes:
Categories of Issues that CC Might Discuss
1. Matters of uncertainty/change of CC authority and process rules
2. PA portfolio administrative issues
3. Permitted, overarching program/portfolio design practices
4. Policy constrained overarching program/portfolio design practices