## Timeline
Energy Savings Assistance Program Solicitations Schedule ALL DATES ARE SUBJECT TO CHANGE |  | 2021 | [7 empty] | 2022 | [51 empty] | 2023
|  | November |  |  |  | December |  |  |  | January |  |  |  |  | Februrary |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  |  | March
|  | 2021-11-17 | 2021-11-24 | 2021-12-01 | 2021-12-08 | 2021-12-15 | 2021-12-22 | 2021-12-29 | 2022-01-05 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27
Regulatory Requirements Ordering Paragraphs of CPUC Decision (D.21-06-015) | [35 empty] | Ordering Paragraph 42: "The Pilot Plus and Pilot Deep program must be launched by the beginning of the third quarter of 2022." | [25 empty] | Ordering Paragraph 123: "The Northern and Southern multifamily whole building programs must begin implementation no sooner than January 1, 2023."
Joint IOU Events | [10 empty] | *Joint IOU Symposium (1/12/2022)
SCE | Main ESA (Basic/Plus) Program | [18 empty] | RFP Release 3/15 |  | Bidder's Conference 3/30 |  |  | Bidder Proposals Due 4/22 | Evaluation and Scoring |  |  | Contract Negotiations | [13 empty] | Contract Awards/ Bidder Notification |  | Program Ramp Up | [16 empty] | Program Launch
| ESA Equipment Vendors | [20 empty] | RFP Release 4/1 |  | Bidder's Conference 4/15 |  |  |  | Bidder Proposals Due 5/10 | Evaluation and Scoring |  | Contract Negotiations | [12 empty] | Contract Awards/ Bidder Notification | Program Ramp Up | [16 empty] | Program Launch
| ESA Inspection | [24 empty] | RFP Release 4/29 |  | Bidder's Conference 5/12 |  |  | Bidder Proposals Due 6/30 | Evaluation and Scoring |  |  |  | Contract Negotiations | [10 empty] | Contract Awards/ Bidder Notification | Program Ramp Up | [13 empty] | Program Launch
| Building Electrification Pilot |  | RFP Release 11/30 | Bidder Conference 12/8 | [6 empty] | Bidder Proposals Due 1/14 | Evaluation and Scoring |  |  |  | Contract Negotiations | [17 empty] | Contract Awards/ Bidder Notification
| Clean Energy Home Pilot |  | RFP Release 12/20 | [7 empty] | Bidder Conference 1/10 |  |  |  | Bidder Proposals Due 2/8 | Evaluation and Scoring |  |  |  | Contract Negotiations | [16 empty] | Contract Awards/ Bidder Notification
| ESA Plus/Deep Pilot (Joint SCE/SCG)** (Dates are based on Advice Letter Approved before 1/31/22) | [12 empty] | RFP Release 2/1 | Bidder Conference 2/8 |  |  |  | Bidder Proposals Due 3/9 | Evaluation and Scoring |  |  | Contract Negotiations | [18 empty] | Contract Awards/ Bidder Notification | Program Ramp Up | [10 empty] | Program Launch 11/9
| Pilot Evaluation** | [12 empty] | RFP Release 2/4 | Bidder Conference 2/11 |  |  |  |  | Bidder Proposals Due 3/14 | Evaluation and Scoring |  |  |  | Contract Negotiations | [18 empty] | Contract Awards/ Bidder Notification
| Interactive Energy Education Note: This timeline is preliminary and subject to change based on future program needs being identified. | [21 empty] | RFP Release/ Bidder Conference | [8 empty] | Contract Negotiations | [12 empty] | Contract Awards/ Bidder Notification | [7 empty] | Design and Implementation | [8 empty] | Program Launch
| ESA System Note: SCE is in the process of exploring options for a new program workflow management system to replace the existing Energy Management Assistance Partnership System (“EMAPS”). This is the current schedule, however it is estimated and subject to change | [8 empty] | RFP Release and Bidder's Conference | [8 empty] | Contract Negotiations | [12 empty] | Conttract Award/ Bidder Notification |  |  |  | Design and Implementation | [25 empty] | Launch New System
SCG | Main ESA (Basic/Plus) Program (delivery of core single-family in-home services) | [13 empty] | Request for Qualification (RFQ) Release 2/11 | Bidders Conference 2/18; RFQ Proposals Due 3/18 |  |  |  |  | RFQ Evaluation/Scoring |  |  |  |  | RFQ Bidder Notifications; RFP Release 4/29 | Bidders Conference 5/6; RFP Proposal Due 6/10 | [5 empty] | RFP Evaluation/Scoring |  |  |  |  | RFP Bidder Notifications; Interviews |  |  |  | Contract Negotiations | [12 empty] | Contract Awards and Issuance/Execute Contract Due 12/30 | [6 empty] | Program Launch
| Customer Experience Technology Platform and Customer Online Audit | [25 empty] | RFP Release 5/6 | Bidders Conference 5/12; Proposal Due 6/17 | [5 empty] | Evaluation/Scoring |  |  |  | Bidder Notification; Interviews |  |  | Contract Negotiations | [5 empty] | Contract Awards and Issuance/Execute Contract Due 9/30 |  | Design/Implementation | [21 empty] | Program Launch 3/6
PG&E (1,2,3,4) | Main ESA (Basic/Plus) Program | RFP released (11/12/21) & Bidders Conference (11/29/21) |  | Bidder Review of RFP, submit RFP Q/A and Proposal Prep | [7 empty] | RFP Proposals Due | Bid Evalution (Scoring, Interviews, Finalist Selection) |  |  |  |  | Contract Negotiations |  |  |  |  | Contract Awards/Issuance |  |  |  | New Program Mobilization
| Multifamily Whole Building Program - REVISED 1.5.2022 | [11 empty] | RFP Release & Bidders Conference | [8 empty] | RFP Proposals Due 3/30 | Bid Evalution (Scoring, Interviews, Finalist Selection) | [12 empty] | Bidder Notification | Contract Negotiations6 | [17 empty] | Contract Awards/Issuance | AL Submission 11/30/22 |  | ED Review of Advice Letter | [7 empty] | Program Ramp Up |  |  |  |  | Program Launch 3/6
| Statewide Multifamily Central Portal |  |  |  |  | RFP released (12/20/21) | Bidder Review of RFP, submit RFP Q/A and Proposal Prep | [7 empty] | RFP Proposals Due | Bid Evalution (Scoring, Interviews, Finalist Selection) |  |  | Contract Negotiations |  |  | Contract Awards/Issuance |  | Program Ramp Up | [31 empty] | New Program Mobilization
| Bulk Materials | [24 empty] | RFP release & Bidders Conference |  | Bidder Review of RFP, submit RFP Q/A and Proposal Prep | [7 empty] | RFP Proposals Due | Bid Evalution (Scoring, Interviews, Finalist Selection) |  |  |  |  | Contract Negotiations |  |  |  | Contract Awards/Issuance |  | Program Ramp Up | [13 empty] | New Program Mobilization
| ESA Pilot Plus/Pilot Deep | [12 empty] | RFP release & Bidders Conference |  | Bidder Review of RFP, submit RFP Q/A and Proposal Prep |  |  |  | RFP Proposals Due | Bid Evalution (Scoring, Interviews, Finalist Selection) |  |  |  | Contract Negotiations | [9 empty] | Contract Awards/Issuance |  | Program Ramp Up |  |  |  |  | New Program Mobilization
SDG&E | Main ESA (Basic/Plus) Program | [17 empty] | *RFP Release (3/1/22) |  | *Bidders Conference (3/11/22) Bidders proposal due 5/2/22 | [6 empty] | Scoring |  |  |  |  | Interviews |  | Scoring | Bidder Notification | Contract Negotiations | [10 empty] | Contract award and issuance 9/30/22 | Program Ramp-Up | [12 empty] | Program Launch (1/1/23)
| ESA Plus/Deep Pilot | [8 empty] | ED Review of AL (Submitted 11/19/21) | Advice letter Approval |  |  |  | RFP Release (2/8/22) Bidders Conference (2/16/22) RFP Due (4/5/22) | [8 empty] | Scoring |  |  | Interviews |  | Bidder Notification | Contract Negotiations | [8 empty] | Contract Award and Issued (7/27/22) | Program Ramp-Up | [13 empty] | Program Launch (11/1/2022)
| Multifamily Whole Building Program | [11 empty] | RFP Release and Bidder's Conference | [8 empty] | RFP Proposals Due | Scoring | [8 empty] | Interviews |  |  | Scoring | Bidder Notification | Contract Negotiations | [17 empty] | *Contract Awards/Issuance (11/16/22) | *Advice Letter Submission (11/30/22) |  | ED Review of Advice Letter | [12 empty] | Program Launch (3/1/2023)
| IT Solutions | [18 empty] | RFP Release (3/15/22) Bidders Conference ( 3/22/22 ) Proposal Due (4/14/22) |  |  |  |  | Scoring |  |  |  |  | Interviews |  | Bidder Notification | Contract Negotiations | [16 empty] | Contract award and issuance (10/11/22) | IT Development | [23 empty] | System Launch 4/1/23
*Tentative Planned Dates as 12/20/2021
** Includes SoCalGas timelines as part of the ESA Program Joint Pilot Deep/Plus and ESA Program Pilot Deep/Plus Evaluation
1. Specific Dates are confidential and provided to registered and approved/qualified bidders only
2. RFP release and activity timelines are subject to change based on needs/outcomes from prior activity
3. ESA Pilot Plus / Pilot Deep timeline contingent on the approval of the PP/PD Implementation Plan Advice Letter
4. Specific Dates have been provided for activities prior to 12/27
CPUC Decision D.21-06-015 is located at: https://docs.cpuc.ca.gov/PublishedDocs/Published/G000/M387/K107/387107687.PDF